## Sheet1
Dell B2B Web App Expansion Communication Plan
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Level of Detail | Audience | Reviewer | Owner
1 | Project Team Communication | Meeting | Ongoing | Weekly | Weekly IT status meeting to discuss schedule, communications, actions, risks & issues | High | IT Project Team | PM | PM
2 | Owners Meeting | Meeting | Ongoing | Monthly | Bi-Weekly status meetings to discuss schedule, communications, actions, risks & issues with impacted user groups | Low | Project Owners, Stakeholders, Project Managers | PM | PM
3 | Stakeholder Update Meeting | Meeting | Ongoing | Monthly | Monthly progress meeting to discuss current project schedule and any changes that may need addressed | Medium | Stakeholders, Project Managers | PM | PM
4 | Department Managers Communication | Email | Ongoing | Weekly | Weekly IT status meeting to discuss schedule, communications, actions, risks & issues | Medium | IT Project Team | PM | PM
5 | Project Update | Email | Ongoing | Weekly | General project update including any deliverables that passed or are coming up. | Medium | Owners, Stakeholders, IT Project Team | PM | PM
6 | Project Turnover Meeting | Meeting | End of Project | One-time | Discuss closeout of project and address any further service agreements | High | Owners | PM | PM
7
8
9
10
11